## Sheet 1 - SYSC 5709 Outstanding
SYSC 5709 Outstanding Tasks
Task | Resp. | Due Date | Status | Comments
Adding Puzzle 1 (Stage 1) | Isaac W | 2020-12-08 | Upload to Github | We need all 3 puzzles for stage 1 before Dec 10 presentation
Adding Puzzle 2 ( Stage 1) | Alvi J. | 2020-12-08 | C
Adding Puzzle 3 (Stage 1) | John J. | 2020-12-08 | N/C
Adding Puzzle 1 (Stage 2) | Isaac W | 2020-12-13 | Upload to Github | All 3 puzzles for stage 2
Adding Puzzle 2 ( Stage 2) | Alvi J. | 2020-12-13 | N/C
Adding Puzzle 3 (Stage 1) | John J. | 2020-12-13 | N/C
Adding Puzzle 1 (Stage 3) | Isaac W | 2020-12-15 | N/C | All 3 puzzles for stage 3
Adding Puzzle 2 ( Stage 3) | Alvi J. | 2020-12-15 | N/C
Adding Puzzle 3 (Stage 3) | John J. | 2020-12-15 | N/C
Presentation Dec 10 | Isaac W, Alvi J. | 2020-12-10 | N/C
Execute Examine | Isaac W | 2020-12-10 | C
Get Reward | Isaac W | 2020-12-10 | N/C
Execute_look() | Isaac W. | 2020-12-10 | C
get_input() | Felix E. | 2020-12-10 | C
has_tag() | Felix E. | 2020-12-10 | C
get_object() | Alvi J. | 2020-12-10 | C
parse_and_execute() | Alvi J. | 2020-12-10 | C
Execute_get() | Alvi J. | 2020-12-10 | C
Display_puzzle_a() | John J. | 2020-12-10 | C
Execute_move() | John J. | 2020-12-10 | C
Execute_hint() | John J. | 2020-12-10 | N/C
Execute_help() | Alvi J. | 2020-12-10 | In Prog.
is_door_unlocked | Alvi J. | 2020-12-17 | N/C
Project wiki | Felix E. And Isaac W. | 2020-12-17 | N/C | Final Work
Testing | John J. | 2020-12-17 | N/C